# Owner’s Special Conditions

662873 Lab Expansion Phase 2

- Project Requirements

The scope of this project includes renovation of an existing Histology Laboratory Open Lab into a Microbiology with supporting work space and AFB BSL-3 Laboratory space. New casework and equipment support systems are being provided throughout the proposed built-out space alongside infrastructure for a processing automation machine. Other impacted areas related to this project are supporting mechanical, electrical, and IT spaces and the roof, as required for the new dedicated rooftop-mounted AHU unit. The project is located on the 4th floor of the UT Southwestern

Clements University Hospital (CUH) building.

1. Project address:				6201 Harry Hines Blvd.

2. Anticipated project start date:		June 8, 2026

3. Project duration:				120 Calendar Day

Primary access for construction will be through loading deck of MMB building to Staff elevator 3.

Work will be performed during normal hours. Activities causing excessive noise and vibration, as well as utility interruptions, may need to be performed after hours or on weekends.

Data communications cabling demolition and installation will be furnished and installed by UTSW. Wireless access points will be salvaged by contractor and turned over to UTSW. In-wall pathways, boxes, and surface mounted raceways for data cabling will be provided by General Contractor.

Security and Access Control devices, pathways, cabling, and hardware will be provided by General Contractor complete per direction of UTSW Access Control.

Audio-visual devices (wall mounted displays) will be provided by UTSW. General Contractor will provide pathways, back-boxes, blocking, mounts, power, and AV cabling to the existing telecom room.

Furniture, Lab Modular and Benches are excluded.

Dumpsters will be provided and managed by the Contractor.

Casework will be part of contractor scope of work

The contractor must provide as built drawings as part of closing documents,

Allowances

- None

Liquidated Damages

0.00

Proprietary Systems

Controls by Siemens Building Technologies

Parking

No free parking.

Parking is as per UTSW parking policy.

Work Hours:

Project normal working hours:  	7am – 5pm

Project working after hours: 	6pm - 6am

Project working weekends hours:	Sat and Sunday

The contractor will be responsible for any overtime and/or weekend work required to maintain the construction schedule. Construction start to be dependent on the delivery of necessary materials.

# Contractor Responsibilities

## General Coordination and Project Management

## Coordination must occur between the Contractor and other work provided and installed by other vendors contracted by UTSW. Although equipment will be supplied and installed by vendors, coordination with vendors and UTSW is crucial.

## The Contractor shall:

- If an electrical shutdown is required, the GC will need to confirm with the UTSW PM if backup power will be required.

- GC is responsible for all final cleaning and waxing of floors.

- Provide spot coolers and backup power as needed to accommodate shutdowns that affect areas that must maintain cool temperatures and power

- Prior to submitting the bid, the Contractor shall examine and compare the contract documents, to the relevant field conditions. Promptly report to the UTSW Project Manager the discovery of any apparent error, omission, or inconsistency in the contract documents.

- Work shall commence at the construction kick-off meeting.

- Utilize only project administration templates provided by UTSW.

- Manage all coordination between the trades, labs, other Contractor’s, Project Managers, equipment vendors, and all other parties involved in the project.

- Perform MEP make-safe prior to abatement. This applies whether the abatement contractor is contracted with UTSW or the general contractor.

- Provide owner training on equipment.

- Request crane permits 4 weeks in advance.

- All traffic control plans must be submitted to UTSW Project Manager and, if applicable, to the City of Dallas Department of Public Works for review and approval prior to blocking traffic lanes or sidewalks. The GC will be responsible for associated fees.

- Provide accessible routes and wayfinding signage for pedestrians, deliveries, UTSW employees, etc.

- Maintain emergency egress for the duration of the project.

- Unused existing lighting to be demoed may not be used as temporary lighting.

- Submit utility interruption paperwork for all subcontractors. A seven (7) day notice is required except for electrical, which requires a two (2) week notification.

- Must field-verify and trace the extent of the MEP system to determine the entirety of the areas/system that will be affected by work and or shutdown. This must be done prior to submitting the notice for a requested systems shutdown. GC will also be required to provide UTSW with an updated systems schedule that reflects the current conditions.

- Submit a pre-punch list to the project manager two (2) weeks prior to scheduling a punch walk with UTSW.

- All interior and exterior work that requires coring, drilling, saw cutting, trenching, etc. the contractor is responsible for all GPR Scans/x-ray scans/DIGTESS prior to work starting. Any damage to underground or concealed utilities or structural reinforcing will be the responsibility of the General Contractor to repair.

- All inspections require seven (7) day notice. Contractor is responsible for submitting the request to the UTSW project manager.

- In addition to the three (3) comprehensive inspections described in Article 12.1.5.3 of the UGCs, UTSW will require five (5) additional inspections:

          - Above ceiling plumbing, mechanical, electrical, and plumbing (MEP) inspection

          - In-wall MEP panels inspection,

          - architectural finishes inspection,

          - personal protective equipment (PPE) inspection prior to energizing electrical work, and,

          - materials testing inspection(s).

The total cost to UTSW of additional inspections resulting from work not being ready for one or more of these inspections is responsibility of Contractor.

- Provide weekly (OAC) meeting minutes and agenda. Agenda & Minutes shall cover but not limited to the below topics:

          - Attendees

          - Construction activities completed this week

          - Construction activities scheduled for next week

          - Coordination topics

          - RFI Log

          - Submittal Log

          - Change orders/change proposal log – Include upcoming potential changes

          - Shutdowns/Utility Interruptions

          - Inspections

          - Safety

          - Unresolved/Pending Issues

          - Updated overall project schedule and 3 weeks look ahead schedule.

- Provide weekly progress reports.

- Submit all submittals within 10 days of receiving a purchase order from UTSW.

## Changes

Change orders issued after execution of the contract must be approved in writing by UTSW authorized signatory, and added/deducted from Purchase Order (PO) prior to commencing work associated with change. Contractor must provide the following documentation with all change orders.

- Updated HUB Subcontracting Plan;

- UTSW Cost Analysis forms for each proposed change (PC);

- Subcontractor and/or Contractor proposal(s) for work associated with each PC;

- Updated drawings and/or specifications created by project Architect for each PC (if applicable);

- Updated Builder’s Risk insurance policy, if approved limit is less than contract amount resulting from change order; and

- Payment & Performance bond rider(s) in new contract amount.

## Work Debris, Scrap Materials and Clean Up

All work debris, scrap and residual materials shall become the property of the Contractor. Work debris and scrap material must be taken to a dumpster at the end of each work day, by the Contractor. Contractor shall, at all times maintain his work area in a clean, safe and professional manner as indicated below.

- All trash buggies/gondolas shall have the wheels cleaned prior to leaving and before entering the construction area and shall be covered as they are moved from and to the dumpster.

- Tacky mats and a damp walk-off mat shall be placed at the exit of the construction area.

- Isolation walls/barriers for dust control and fire separation shall be provided as required by the Project Manager. If not clearly called out in the Construction Documents it shall be the Contractor’s responsibility to obtain clarification before submitting bid.

- UTSW shall provide dumpsters for all trash and debris.

## Safety

Contractor shall strictly adhere and comply with all Occupational Safety and Health Standards (OSHA), UTSW Contractor Safety Guidelines, and other applicable safety practices as they pertain to the protection of personnel, property and equipment.

- Contractor shall submit Safety Data Sheets (SDS) for any chemicals that can generate hazardous or nuisance vapors, particulate, mist, or odors that will be used in active clinical/hospital areas to OSBC prior to starting work.

- Contractor shall schedule and manage weekly safety meetings on the project.

- Contractor shall post all necessary construction signage with emergency contacts.

- Negative air machine(s) for dust control in the construction area shall be present at all times. Filters shall be changed per Manufacturer’s recommended maintenance plan. HEPA filter shall be new, and unused before the start of work. Contractor shall replace filter at the request of the UTSW project manager.

- Coordination of make-safe for all utilities with UTSW Project Manager before demolition starts.

- All personnel working in the construction area shall have a UTSW issued work badge and current UTSW safety training.

- Whenever the UTSW Representative becomes aware of any noncompliance with specifications or any conditions which poses a serious or imminent danger to the health and safety of the public or UTSW personnel, the UTSW Representative shall request the contractor to stop work until an action plan that corrects the situation is approved by the UTSW Representative. If the Contractor fails or refuses to promptly take corrective action the UTSW Representative issue an order to stop all or part of the work until satisfactory corrective action has been taken.

- Contract shall supply UTSW visitor’s new hard hats and safety glasses when visiting the job site.

## Approval and Communications

During the bidding process, all questions shall be emailed to Marcus Howard with the Project Manager copied Mohammed.Salama@utsouthwestern.edu

The Contractor shall work under the direction of the UTSW Hospital Facilities project manager who will determine if the work has been completed in accordance with the specifications.  Upon award, the general contractor’s project manager shall email any/all questions, change order requests, room closure requests, utility interruptions notices or overtime/week-end work requests to the UTSW designated PM.

## Proposal

Contractor shall review the construction documents and address any drawing/specification conflicts and constructability issues with UTSW prior to submitting bid proposal.

The Contractor shall

    - Provide cost proposal as described by Owner.

    - Include identified VE opportunities as alternates proposed to Owner (if applicable).

    - Exclude TAB from their pricing.

    - Provide pricing for all alternates. (If applicable)

END OF DOCUMENT